## 1.16.25 Cost per bldg
Rogers Phase 3 - 1.16.25 | Octoplex P |  | Quadplex O |  | Pricing/Quantity notes | 11.21.25
Trade Break Down | Material | Labor | Material | Labor
Slab Concrete and Labor | 8129 |  | 11555 |  | Part of Rey's contract | Need estimates for quantities per slab
Foundation Packet | 3500 |  | 4000 |  | Our average cost per slab on P3 was $1161.96 BUT all rebar itself was already on hand. | Need updated take off from Tool Source or other
Driveway/Sidewalks/Flatwork | 1770 |  | 1770 |  |  | Need estimated quatities
Pump Truck |  | 701.25 |  | 701.25 | FIrst pour - six slabs - 9.5 hours
Permits |  |  |  |  | Already paid by Resortments
Compaction Test |  | 60 |  | 60
Termite Treatments |  | 275 |  | 275 | West Termite
Column Posts | 1400 |  | 1400 |  | We have 50 of these left from P2 to take | Verify Specifications and are we using?
Framing | 26688 | 26976 | 32639.78 | 22056 | Make sure firewall in here on labor
Roofing | 4500.61 | 1885 | 5399.88 | 2080 | Lansing material and Walter labor pricing @65/sqaure | Verify # of squares and color
Simpson Ties | 1991.51 |  | 1752.31 |  | Ridout - will deliver 1/19
Exterior Stairwell system | 1928.43 |  |  |  |  | China??
Exterior Stairwell Metal |  |  |  |  | STILL NEED METAL PICKETS
Ext. siding Smart Siding | 14421.58 | 15500 | 18542.68 | 12250 | Roughly 420/bldg for delivery | Verify color scheme
Thermowood | 4964 |  | 4113.6 |  | Actual thermowood came in way higher. Trying 1 P quad with Macadamia b&b, and T & G soffit material. Cost for this P is $718.32 for the T/G soffit and 3687.18 for added siding. Total is 4405.50. If we like it, will make formal change.
Stucco |  | 3000 |  | 3000 | Reduced - not much stucco
Beams | [5 empty] | We have a little material left to take on both projects than we should not order more.
Gutters | 1525 |  | 1500 |  |  | Verify 5" and style
Corrugated Pipe for Gutters | 100 |  | 100 |  |  | Bury into ground - part of landscape contract
Landscaping | 2500 |  | 2500 |  |  | Luis for labor then just need materials
Plumbing | 21000 | 28000 | 18400 | 18000 | Ivin - Legacy labor - need materials - estimated numbers | Chris/Legacy
Slab $6125.14/$4,097.51
Top
Trim
Upinor |  |  | 7897.59 |  |  | Chris/Legacy
Commercial Fire System |  | 27326 |  |  |  | Anyone know who bid this for the P's? Can we stick with Upinor for Q since not stacked?
Linear Exterior Lights | 255.56 |  | 255.56 |  | Q - 4, P - 4, O - 4 $63.89 each | Verify not Needed
Vanity Lights | 420.08 |  | 420.08 |  | Q - 10 3lite, P-8 3 lite, O-8 3lite | 3lite $52.51, 5lite $75.54
Dusk to Dawn Lights | 39.98 |  | 39.98 |  | Lowes
Ceiling Fans | 1467 |  | 1100 |  | P - 16 O - 12 Lowes | Need to be able to adjust speed
Down Rods for fans | 228 |  | 180 |  | only need 1 ft downrods
Coach Lights (gooseneck) | 369.2 |  | 147.68 |  | Q - 6, 0 - 4, P - 10 | 36.92 each - upstairs balcony lights?? Are what?
Mechanical |  | 3500 |  | 3500 |  | Barger had done this previously. Might could get him back with a Bump in pay. (chris)
Electrical | 401.91 | 47949 | 401.91 | 47949 | Material Add for Data Pex .74/ft | Grejada or other options.
PTAC | 10104 |  | 13128 |  | Amana or Hotpoint Wall tstat or no? Price shown is Hotpoint, no tstat. Cheapest option | Are we sticking with lowest price point or working for a nicer appeal?
Insulation |  | 8500 |  | 8500 |  | Johnny
Firerock | 2593.4 | 0 | 3262.66 | 0 | Needs to be within the framing labor | Need projected material quantities
Drywall | 7500 | 16000 | 7500 | 14352 |  | Need projected material quantities
Mud/Tape/Texture/CB |  |  |  |  | Need a material takeoff | Need estimate based off above info
Interior Paint | 3000 | 4000 | 3000 | 3500 |  | Need to decide colors (have a little time) and estimate the gallons needed
Exterior Paint | [5 empty] | Doors - what color? Also allow a little for siding touch ups as needed
Trim | 1788.9 | 4000 | 1773.13 | 3800 |  | MDF. 6 in? Keep trim same colors as walls? Need to know as will play into paint costs.
Exterior Doors | 3517.53 |  | 1300.86
Interior Doors | 2571.1 |  | 5054.43 |  |  | Need to review Quad P interior doors
Stairwell Railings/mop board | 0 |  | 923.76 |  |  | Estimated based on O plan (six stariwells)
Windows | 16212.72 |  | 15007.19 |  |  | Currently using Lansing - do we want to try China? Not sure we have time to get them here.
Window tape, trim coil, flashing | 481.81 |  | 481.81 |  | Trim Coil is 481.81 per bldg, zip tape is | Make sure to allow for this
Door Knobs and locks |  | 700 |  | 700 |  | Need updated takeoff here. Might need to spend more to stay US. Have had a lot of issue with China product.
Ext Knob deadbolt Combo | 196.02 |  | 71.28 |  | P-11, Q-6, O-4 $17.82/each
Privacy Lever | 64 |  | 128 |  | P-8, Q-18, O-16 $8.00/each
Dummy Lever | 0 |  | 112.32 |  | P-0, Q-8, O-16 $7.02 each
Passage Lever | 0 |  | 32 |  | P-0, Q-6, O-4 $8.00/each
Hinge Pin Stops | 26.22 |  | 60.72 |  | P-19, Q-38, O-44 $1.38/each
Cabinet Pulls | 287.64 | 200 | 226.44 | 200 | $1.53/each | 148 per O, 188 per P, 132 per Q (?)
Bath Hardware Package | 173.6 | 200 | 173.6 | 200 | $21.70/set P-8, Q-10, O-8 | China - verify quantities per quad
Towel Ring |  |  |  |  | 6.18
Toilet Paper Holder |  |  |  |  | 6.18
Towel Bar |  |  |  |  | 9.34
Cabinets | 8621.05 | 4800 | 7232.83 | 3500 |  | China - verify quantities per quad. Do we have Q quote?
Countertops | 4970.7 | 4500 | 4052.91 | 3400 | 12.63/ft | China - verify quantities per quad. Do we have Q quote?
LVT | 6487.2 | 5500 | 5618 | 4779 | reduction of quantity | The P is LVT throughout - we will need to either soundproof upsatirs or carpet some areas
Carpet |  |  |  |  | 2nd floor of P's
Nosing for Stairwells | 0 |  | 125 |  |  | China - verify quantties per quad. Applicable for interior stairwells on O and Q
Kitchen Sinks | 1508.32 |  | 1131.24 |  | $188.54/sink P - 8, Q - 6, O - 4
Vanity Sinks | 358.4 |  | 358.4 |  | $44.80/sink P-8, Q-10, O-8
Closet Kits | 8626.48 |  | 4622.8 |  |  | Prices are from 7.29.25 - need to verify and need Q price
Appliances | 30046.45 |  | 9815.49 |  | Note that the Farco number was in here but after examination, it did NOT include tax. Updated to include tax. | Have been using Metro. Typically the best price.
Mirrors | 665.76 |  | 665.76 |  | 36x24 $83.22 P-8, Q-10, O-8
Blinds | 1738 |  | 1010.5 |  |  | China - verify sizes - this has been a huge issue of not having enough. We need to double check which windows we have blinds on and call those out on plans.
Luis
Cleaning |  | 1000 |  | 1000 |  | Luis cleaners
Water Hookup ( Meter) | [5 empty] | Zac please verify pricing
Sanitation units | 450 |  | 450 |  |  | Portapotties needed for the site x 12 / # of units
Dumpster | 500 |  | 500
House Numbers | 200 |  | 200 |  |  | Need to understand how they are making us number these buildings and how many sets of the same number we need. Price out - weirdly hard to get ahold of enough reflective numbers. Need a bulk order from Lowes or someone. Possibly even reach out to Wade.
Total Cost to Build | 210289.16 | 204572.25 | 202135.18 | 153802.25
|  | 414861.41 | 355937.43
Materials include tax where applicable
China

## Phase 3 actual cost
Rogers Phase 3 - 12.22.25 | Octoplex P |  | Quadplex O |  | Pricing/Quantity notes | 11.21.25
Trade Break Down | Material | Labor | Material | Labor
Slab Concrete and Labor | 8129 |  | 11555 |  | Part of Rey's contract | Need estimates for quantities per slab
Foundation Packet |  |  |  |  | Adjusting quote | Need updated take off from Tool Source or other
Driveway/Sidewalks/Flatwork | 1770 |  | 1770 |  |  | Need estimated quatities
Pump Truck |  | 600 |  | 600 | Smaller slab- pour 4-5 at a time
Permits |  |  |  |  | Already paid by Resortments
Compaction Test |  | 60 |  | 60
Termite Treatments |  | 300 |  | 300
Column Posts |  |  |  |  | We have 50 of these left from P2 to take | Verify Specifications and are we using?
Framing | 26686.76 | 26976 | 32639.78 | 22056 | Make sure firewall in here on labor
Roofing | 4500.61 | 1885 | 5399.88 | 2080 | Lowe's working on a take off | Verify # of squares and color
Exterior Stairwell system | 1928.43 |  |  |  |  | China??
Exterior Stairwell Metal |  |  |  |  | STILL NEED METAL PICKETS
Ext. siding Smart Siding | 14421.58 | 15500 | 18542.68 | 12250 | Roughly 420/bldg for delivery | Verify color scheme
Thermowood | 4964 |  | 4113.6 |  | Actual thermowood came in way higher. Trying 1 P quad with Macadamia bord and batt, and tongue and groove soffit material. Cost for this P is $718.32 for the T/G soffit and 3687.18 for added siding. Total is 4405.50. If we like it, will make formal change.
Stucco |  | 3000 |  | 3000 | Reduced - not much stucco
Beams | [5 empty] | We have a little material left to take on both projects than we should not order more.
Gutters | 1525 |  | 1500 |  |  | Verify 5" and style
Corrugated Pipe for Gutters | 100 |  | 100 |  |  | Bury into ground - part of landscape contract
Landscaping | 2500 |  | 2500 |  |  | Luis for labor then just need materials
Plumbing | 21000 | 22000 | 18400 | 18000 | Ivin - Legacy labor - need materials - estimated numbers | Chris/Legacy
Slab $5429.43/$4,048.34
Top
Data Pex
Upinor |  |  | 10000 |  |  | Chris/Legacy
Commercial Fire System |  | 27326 |  |  |  | Anyone know who bid this for the P's? Can we stick with Upinor for Q since not stacked?
Linear Exterior Lights |  |  |  |  | Q - 4, P - 4, O - 4 $63.89 each | Verify not Needed
Vanity Lights |  |  |  |  | Q - 10 3lite, P-8 3 lite, O-8 3lite | 3lite $52.51, 5lite $75.54
Dusk to Dawn Lights | 39.98 |  | 39.98 |  | Lowes
Ceiling Fans | 1467 |  | 1100 |  | P - 16 O - 12 Lowes | Need to be able to adjust speed
Down Rods for fans | 228 |  | 180 |  | only need 1 ft downrods
Coach Lights (gooseneck) |  |  |  |  | Q - 6, 0 - 4, P - 10 | 36.92 each - upstairs balcony lights?? Are what?
Mechanical |  | 3500 |  | 3500 |  | Barger had done this previously. Might could get him back with a Bump in pay. (chris)
Electrical | 401.91 | 47949 | 401.91 | 47949 | Data Pex Add | Grejada or other options.
PTAC | 10152 |  | 10152 |  | Amana or Hotpoint Wall tstat or no? Price shown is Hotpoint, no tstat. Cheapest option | Are we sticking with lowest price point or working for a nicer appeal?
Insulation |  | 8500 |  | 8500 |  | Johnny
Firerock | 2593.4 | 0 | 3262.66 | 0 | Needs to be within the framing labor | Need projected material quantities
Drywall | 7500 | 16000 | 7500 | 14352 |  | Need projected material quantities
Mud/Tape/Texture/CB |  |  |  |  | Need a material takeoff | Need estimate based off above info
Interior Paint | 3000 | 4000 | 3000 | 3500 |  | Need to decide colors (have a little time) and estimate the gallons needed
Exterior Paint | [5 empty] | Doors - what color? Also allow a little for siding touch ups as needed
Trim | 1788.9 | 4000 | 1773.13 | 3800 |  | MDF. 6 in? Keep trim same colors as walls? Need to know as will play into paint costs.
Exterior Doors | 3517.53 |  | 1300.86
Interior Doors | 2571.1 |  | 5054.43 |  | Removed some barn doors from P plan | Need to review Quad P interior doors
Stairwell Railings/mop board | 0 |  | 923.76 |  |  | Estimated based on O plan (six stariwells)
Windows | 16212.72 |  | 15007.19 |  |  | Currently using Lansing - do we want to try China? Not sure we have time to get them here.
Window tape, trim coil, flashing | 481.81 |  | 481.81 |  | Avg cost per phase | Make sure to allow for this
Door Knobs and locks |  | 700 |  | 700 |  | Need updated takeoff here. Might need to spend more to stay US. Have had a lot of issue with China product.
Ext Knob deadbolt Combo |  |  |  |  | P-11, Q-6, O-4 $17.82/each
Privacy Lever |  |  |  |  | P-8, Q-18, O-16 $8.00/each
Dummy Lever |  |  |  |  | P-0, Q-8, O-16 $7.02 each
Passage Lever |  |  |  |  | P-0, Q-6, O-4 $8.00/each
Hinge Pin Stops |  |  |  |  | P-19, Q-38, O-44 $1.38/each
Cabinet Pulls |  | 200 |  | 200 | $1.53/each | 148 per O, 188 per P, 132 per Q (?)
Bath Hardware Package |  | 200 |  | 200 | $21.70/set P-8, Q-10, O-8 | China - verify quantities per quad
Towel Ring |  |  |  |  | 6.18
Toilet Paper Holder |  |  |  |  | 6.18
Towel Bar |  |  |  |  | 9.34
Cabinets |  | 4800 |  | 3500 |  | China - verify quantities per quad. Do we have Q quote?
Countertops |  | 4500 |  | 3400 | 12.63/ft | China - verify quantities per quad. Do we have Q quote?
LVT |  | 5500 |  | 4779 | reduction of quantity | The P is LVT throughout - we will need to either soundproof upsatirs or carpet some areas
Carpet |  |  |  |  | 2nd floor of P's
Nosing for Stairwells | 0 |  |  |  |  | China - verify quantties per quad. Applicable for interior stairwells on O and Q
Kitchen Sinks |  |  |  |  | $188.54/sink P - 8, Q - 6, O - 4
Vanity Sinks |  |  |  |  | $44.80/sink P-8, Q-10, O-8
Closet Kits | [5 empty] | Prices are from 7.29.25 - need to verify and need Q price
Appliances | 30046.45 |  | 9815.49 |  | Based on current Metro pricing | Have been using Metro. Typically the best price.
Mirrors |  |  |  |  | 36x24 $83.22 P-8, Q-10, O-8
Blinds | [5 empty] | China - verify sizes - this has been a huge issue of not having enough. We need to double check which windows we have blinds on and call those out on plans.
Luis
Cleaning |  | 1000 |  | 1000 |  | Luis cleaners
Water Hookup ( Meter) | [5 empty] | Zac please verify pricing
Sanitation units | 450 |  | 450 |  |  | Portapotties needed for the site x 12 / # of units
Dumpster | 500 |  | 500
House Numbers | 200 |  | 200 |  |  | Need to understand how they are making us number these buildings and how many sets of the same number we need. Price out - weirdly hard to get ahold of enough reflective numbers. Need a bulk order from Lowes or someone. Possibly even reach out to Wade.
Total Cost to Build | 168676.18 | 198496 | 167664.16 | 153726
|  | 367172.18 | 321390.16
Materials include tax where applicable |  | 4406066.16 | 1928340.96 |  | 6334407.12 |  | 12 P and 6 O
China |  |  |  |  | 279198.99 |  | China Order
Actual to order in total to finish P3 |  |  |  |  | 6000 |  | Posts from Ridout to finish
Door hardware |  | 1197.18 |  |  | 20915.3 |  | Rebar to finish
Bath Hardware |  | 0 |  |  | 6640521.41 |  | Vertical Cost for phase 3 per cost sheet on 12.22
Vanity Sinks |  | 0
Kitchen Sinks |  | 9804.08 |  |  | 6800000 |  | Allotted
3 lite vanity light |  | 0 |  |  | 159478.59 |  | Margin of error
gooseneck coach lights |  | 5538 |  |  | 8859.9217 |  | per bldg margin of error
exterior vertical sconce lights |  | 5238.98
mirrors |  | 0
Cabinet Pulls |  | 296.82
LVT |  | 0
Granite |  | 51154.66
Cabinets |  | 54376.67
Blinds |  | 12991.88
Closet Kits |  | 130800.72
Truck to Rogers |  | 7800
279198.99

## Materials
Rogers Phase 3 - 12.17.25 | P | O |  |  |  | Pricing/Quantity notes
Trade Break Down | Material | Material | Supplier | AMEX | Status
Slab Concrete and Labor | 8129 | 11555 | Eagle RediMix - Frankie - 479-228-4570 | Yes - No fee | managed - Jeremy | Need estimates for quantities per slab
Foundation Packet | 3500 | 4000 | Tool Source - Mark Webb - 501-760-5000 | Yes but fee | Locked | Need updated take off from Tool Source or other
Driveway/Sidewalks/Flatwork | 1770 | 1770 | Eagle RediMix - Frankie - 479-228-4570 waiting to hear back |  | managed - Jeremy | Need estimated quatities
Column Posts | 1400 | 1400 | Ridout - Adam Treece - 501-422-9152 Amex 2% charge | Yes - 2% charge | Locked | Verify Specifications and are we using?
Framing | 26686.76 | 32639.78 | Ridout |  | managed - Jeremy
Roofing | 2810 | 3500 | Lowes or Lansing - Del (lowes) 479-200-1236/ Ethan (Lansing) 573-391-3064 | Lowes - yes - no fee, Lansing yes - 2% | managed - Jeremy | Verify # of squares and color
Exterior Stairwell system | 1607.35 |  | Ridout
Exterior Stairwell Metal |  |  | ???
Ext. siding Smart Siding | 14421.58 | 18542.68 | Carolina Colortones - Guy Campbell - 828-779-0028 | Yes but 3% fee | Locked - material managed - J | Verify color scheme
Thermowood | 4964 | 4113.6 | Lumber Plus- Alexia Garcia 281-915-0770 ext 1021 | Yes - No fee | managed - Jeremy
Gutters | 1525 | 1500 | This is provided by company that installs |  |  | Verify 5" and style
Corrugated Pipe for Gutters | 100 | 100 | Lowes? |  |  | Bury into ground - part of landscape contract
Landscaping | 2500 | 2500 | Sod Store - Hunter - 479-619-7256 | Yes No fee through quick books | materials managed - Jeremy | Luis for labor then just need materials
Plumbing | 21000 | 18400 | Plumbing Warehouse? Mason Parr | Yes no fee |  | Chris/Legacy
Slab $5429.43
Upinor |  | 10000 | Upinor? |  |  | Chris/Legacy
Commercial Fire System | [5 empty] | Anyone know who bid this for the P's? Can we stick with Upinor for Q since not stacked?
Linear Exterior Lights | 255.56 | 255.56 | China |  | Locked | Verify not Needed
Vanity Lights | 420.08 | 420.08 | China |  | Locked | 3lite $52.51, 5lite $75.54
Dusk to Dawn Lights | 39.98 | 39.98 | Lowes |  | Locked
Ceiling Fans | 1467 | 1100 | Lowes |  | Locked | Need to be able to adjust speed
Down Rods for fans | 228 | 180 | Lowes |  | Locked
Coach Lights (gooseneck) | 369.2 | 147.68 | China |  |  | 36.92 each - upstairs balcony lights?? Are what?
PTAC | 10152 | 10152 | PTAC Direct - Anuj or Eric 877.454.7822 AJ 502-350-3949 Eric | Yes - 1 % fee |  | Amana vs hotpoint vs tstat or no
Firerock | 2593.4 | 3262.66 | LW Supply - Steve Or David - 479-878-2700 | Yes, they think no fee | managed - Jeremy | Need projected material quantities
Drywall | 7500 | 7500 | LW Supply | Yes, they think no fee | managed - Jeremy | Need projected material quantities
Mud/Tape/Texture/CB |  |  | LW Supply | Yes, they think no fee | managed - Jeremy | Need estimate based off above info
Interior Paint | 3000 | 3000 | Sherwin Williams - Scott Weber - 479-936-0126 | Yes - no fee | managed - Jeremy | Need to decide colors (have a little time) and estimate the gallons needed
Exterior Paint |  |  | Sherwin Williams - Scott Weber - 479-936-0126 |  | locked | Doors - what color? Also allow a little for siding touch ups as needed
Trim | 1788.9 | 1773.13 | Ridout | Yes - 2% | locked | MDF. 6 in? Keep trim same colors as walls? Need to know as will play into paint costs.
Exterior Doors | 3517.53 | 1300.86 | Ridout | Yes - 2% | locked
Interior Doors | 2571.1 | 5054.43 | Ridout | Yes - 2% | locked | Need to review Quad P interior doors
Stairwell Railings/mop board | 0 | 923.76 | Ridout | Yes - 2% | locked | Estimated based on O plan (six stariwells)
Windows | 16212.72 | 15007.19 | Lansing - Ethan 573-391-3064 | Yes - 2% |  | Currently using Lansing - do we want to try China? Not sure we have time to get them here.
Window tape, trim coil, flashing |  |  | Lansing | Yes - 2% |  | Make sure to allow for this
Door Knobs and locks |  |  | China |  | locked | Need updated takeoff here. Might need to spend more to stay US. Have had a lot of issue with China product.
Ext Knob deadbolt Combo | 196.02 | 71.28 |  |  | locked
Privacy Lever | 64 | 128 |  |  | locked
Dummy Lever | 0 | 112.32 |  |  | locked
Passage Lever | 0 | 32 |  |  | locked
Hinge Pin Stops | 26.22 | 60.72 |  |  | locked
Cabinet Pulls | 287.64 | 226.44 | China |  | locked | 148 per O, 188 per P, 132 per Q (?)
Bath Hardware Package | 173.6 | 173.6 | China |  | locked | China - verify quantities per quad
Towel Ring |  |  |  |  | locked
Toilet Paper Holder |  |  |  |  | locked
Towel Bar |  |  |  |  | locked
Cabinets | 8621.05 | 7232.83 | China |  | locked | China - verify quantities per quad. Do we have Q quote?
Countertops | 4970.7 | 4052.91 | China |  | locked | China - verify quantities per quad. Do we have Q quote?
LVT | 6487.2 | 5618 | China |  | locked | The P is LVT throughout - we will need to either soundproof upsatirs or carpet some areas
Carpet |  |  | ????
Nosing for Stairwells | 0 | 125 | China |  | Locked | China - verify quantties per quad. Applicable for interior stairwells on O and Q
Kitchen Sinks | 1508.32 | 1131.24 | China |  | Locked
Vanity Sinks | 358.4 | 358.4 | China |  | Locked
Closet Kits | 9479.2 | 5944.52 | China |  | Locked | Prices are from 7.29.25 - need to verify and need Q price
Appliances | 27112 | 8420 | Metro - Billy McKinney - 479-301-3771 | Yes - 3% | Locked | Have been using Metro. Typically the best price.
Mirrors | 665.76 | 665.76 | China |  | Locked
Blinds | 1738 | 1010.5 | China |  | Locked | China - verify sizes - this has been a huge issue of not having enough. We need to double check which windows we have blinds on and call those out on plans.
Luis
Cleaning | [5 empty] | Luis cleaners
Water Hookup ( Meter) | [5 empty] | Zac please verify pricing
Sanitation units | 450 | 450 | Arkansas Portables - 479-770-5577 | Yes - No fee right now |  | Portapotties needed for the site x 12 / # of units
Dumpster | 500 | 500 | LRS - Brittany - 479-601-5025 | Yes - said $2.95 fee
House Numbers | 200 | 200 | Lowes | Yes - no fee
Total Cost to Build | 203367.27 | 196651.91
Materials include tax where applicable
China
Still Determining
Will take AmEx No Fee per phone call

## Labor
Rogers Phase 3 - 12.17.25 11:32 PM | P | O |  |  | O
Trade Break Down | Labor | Labor | Sub | Contact
Slab Concrete and Labor |  |  | Rey |  | Part of Rey's contract
Foundation Packet |  |  | Rey |  | Adjusting quote
Driveway/Sidewalks/Flatwork |  |  | Rey
Pump Truck | 600 | 600 | Brundage Bone |  | Smaller slab- pour 4-5 at a time
Permits |  |  |  |  | Already paid by Resortments
Compaction Test | 60 | 60 | MTA
Termite Treatments | 300 | 300 | West |  | Pre or post slab
Framing | 26976 | 22056 |  |  | Make sure firewall in here.
Roofing | 1610 | 2500 |  |  | Lowe's working on a take off
Ext. siding Smart Siding | 15500 | 12250 |  |  | Roughly 420/bldg for delivery
Thermowood |  |  |  |  | Farco material numbers
Stucco | 3000 | 3000 | ??? |  | Reduced - not much stucco
Beams
Gutters
Corrugated Pipe for Gutters
Landscaping
Plumbing | 22000 | 18000 | Legacy |  | Ivin - Legacy labor - need materials - estimated numbers
Commercial Fire System | 27326
Mechanical | 3500 | 3500
Electrical | 45000 | 40512.3
PTAC |  |  |  |  | estimated from PTAC direct - 12 of the 12k per quad
Insulation | 8500 | 8500
Firerock | 0 | 0 |  |  | Needs to be within the framing labor
Drywall | 16000 | 14352
Mud/Tape/Texture/CB |  |  |  |  | Need a material takeoff
Interior Paint | 4000 | 3500
Exterior Paint
Trim | 4000 | 3800
Door Knobs and locks | 700 | 700
Ext Knob deadbolt Combo |  |  |  |  | P-11, Q-6, O-4 $17.82/each
Privacy Lever |  |  |  |  | P-8, Q-18, O-16 $8.00/each
Dummy Lever |  |  |  |  | P-0, Q-8, O-16 $7.02 each
Passage Lever |  |  |  |  | P-0, Q-6, O-4 $8.00/each
Hinge Pin Stops |  |  |  |  | P-19, Q-38, O-44 $1.38/each
Cabinet Pulls | 200 | 200 |  |  | $1.53/each
Bath Hardware Package | 200 | 200 |  |  | $21.70/set P-8, Q-10, O-8
Towel Ring |  |  |  |  | 6.18
Toilet Paper Holder |  |  |  |  | 6.18
Towel Bar |  |  |  |  | 9.34
Cabinets | 4800 | 3500
Countertops | 4500 | 3400 |  |  | 12.63/ft
LVT | 5500 | 4779 |  |  | reduction of quantity
Carpet |  |  |  |  | 2nd floor of P's
Closet Kits |  |  |  |  | Too high - where else can we buy
Appliances |  |  |  |  | Based on current Metro pricing
Mirrors |  |  |  |  | 36x24 $83.22 P-8, Q-10, O-8
Blinds
Luis
Cleaning (Luis) | 1000 | 1000
Water Hookup ( Meter)
Sanitation units
Dumpster
House Numbers
Total Cost to Build | 195272 | 146709.3
Materials include tax where applicable
China